CALL FOR EXPRESSIONS OF INTEREST (EOI)

Consultancy Services: Baseline Evaluation for Strengthening Agroecology-Based School & College Meal Systems in East and Southern Africa Project

1. Introduction

- Procuring Entity

The Alliance for Food Sovereignty in Africa (AFSA) is the largest network of civil society organisations (CSOs) on the African continent, dedicated to advancing agroecology and food sovereignty across Africa. AFSA unites a rich and diverse membership, including African food producer networks, CSO networks, indigenous people's organisations, faith-based organisations, women's and youth groups, consumer movements, and international organisations,  all committed to a shared, transformative mission. With 48 member organisations operating across 50 African countries, AFSA directly influences the lives of approximately 200 million people. Through evidence-based advocacy, grassroots mobilisation, and pan-African campaigns, AFSA champions the rights of smallholder farmers, promotes biodiversity, and promotes food systems rooted in African knowledge and ecological integrity.

AFSA, in partnership with partners in Uganda, Kenya, and Malawi, is implementing a research project titled “Strengthening Agroecology-Based School and College Meal Systems in East and Southern Africa."

- Background about the project

School and college feeding programmes in East and Southern Africa are essential for improving nutrition, school attendance, and learning outcomes, especially for learners from low-income households. However, many feeding initiatives face persistent constraints that weaken their impact and sustainability. Common challenges include unstable food supply, high dependence on conventional markets, weak links between schools and local producers, and inconsistent financing. As a result, schools may struggle to access fresh, diverse, and nutritious foods, while local smallholder farmers, particularly women and youth, remain underutilised as reliable suppliers. Climate-related shocks and environmental degradation further affect production and supply reliability, increasing vulnerability across already fragile systems. In addition, the policy and institutional environment for school feeding and public procurement is often fragmented and not sufficiently responsive to gender equality and social inclusion, limiting community participation and equitable benefit-sharing.

To respond to these gaps, AFSA, with funding from the International Development Research Centre (IDRC), is leading the Strengthening Agroecology-Based School & College Meals Systems in East and Southern Africa Project. The project is implemented in Uganda, Kenya, and Malawi. The project uses a Participatory Action Research (PAR) approach and a Gender, Equality, and Social Inclusion (GESI) lens to (i) assess how existing school and college models affect socio-economic dynamics in communities; (ii) pilot and refine agroecology-based school meal models with stakeholders; and (iii) generate evidence-based recommendations for policy integration and scaling.

The project is expected to contribute to stronger and more gender-responsive farmer–school linkages, improved access to safe and nutritious agroecological food for learners, increased market opportunities and incomes for smallholder farmers (especially women and youth), and a more enabling policy environment for sustainable and inclusive provision of school meals.

As a first step in implementing the project, AFSA seeks to commission a baseline evaluation/survey to further inform the project's design, learning, and implementation.

2. Purpose of the Assignment

The purpose of the assignment is to carry out a baseline evaluation of existing school meal systems across selected sites in the three countries.

The baseline will: a) Provide benchmark data for monitoring and evaluation; b) Identify gaps, opportunities, and contextual dynamics; c) Inform the co-design of agroecological school meal models, and d) Support future impact evaluation

3. Objectives of the Baseline Study

- Overall Objective

To generate robust baseline data on school meal systems, agroecological food procurement, and socio-economic dynamics to guide project implementation and evaluation.

- Specific Objectives

The consultant/team will:

- Assess existing school meal systems and food provision models

- Analyze food sourcing systems and supply chains

- Evaluate farmer–school linkages for the different school meal models

- Examine gender equality and social inclusion (GESI) dimensions for each school meal model

- Assess economic opportunities and constraints for smallholder farmers, especially women and youth

- Review policy, institutional, and governance frameworks linked to school meals

- Develop baseline indicators aligned with the project MEAL framework

4. Scope of Work

The baseline will cover selected study sites across Uganda, Kenya, and Malawi, representing different school feeding models. Key tasks include: a) Conduct an inception phase (methodology refinement, stakeholder consultations); b) Undertake a comprehensive literature and policy review; c) Design and validate data collection tools; d) Conduct field data collection; e) Perform data analysis (quantitative and qualitative); f) Facilitate stakeholder validation workshops; and g) Produce a comprehensive baseline report

5. Methodology

The consultant/team is expected to propose a rigorous methodology, including study design, data collection methods and data analysis. The methodology proposed should allow for future impact evaluation approaches.

6. Key Deliverables

The consultant/team will deliver, among others: a) Inception Report (methodology, tools, and work plan); b) Data Collection Tools and protocols; c) Clean and documented datasets; d) Draft Baseline Report, e) Validated Final Baseline Report, and f) Presentation of findings to the implementing partners in the three countries.

7. Duration of the Assignment

The assignment is expected to take 2 months, starting from the date of contract signing. The assignment is 100% virtual.

8. Institutional Arrangements

The consultant/team will work closely with AFSA’s a) Programme Officer – Research; b) Programme Coordinator – Land, Soil & Agroecology; c) Programme Coordinator – M&E; and d) implementing country partners. AFSA will provide overall coordination and technical oversight.

9. Required Qualifications and Experience

The consultant/team should demonstrate:

- Proven experience in baseline studies and evaluations

- Expertise in agriculture, agroecology, or food systems

- Strong experience in mixed-methods research

- Demonstrated understanding of  PAR and GESI

- Experience working in East and/or Southern Africa

- Strong analytical and report-writing skills

- Experience with school and college meal systems is an added advantage.

10. Ethical Considerations

The consultant must adhere to the following: a) International research ethics standards;  b) Informed consent procedures; c) Confidentiality and data protection; and d) Safeguarding of children and vulnerable groups.

11. Submission Requirements

Interested consultants/teams should submit:

- Technical proposal

- Financial proposal (detailed budget in USD)

- Company/consultant profile

- Relevant experience and references

- CVs of key personnel

12. Submission Details

- Deadline: 16th June 2026, at 5 pm East African Time. Late submissions will not be considered.

- Submission email: afsa@afsafrica.org

- Subject line: EOI – Baseline Evaluation Agroecology School Feeding Project

13. Evaluation Criteria

Proposals will be assessed based on the following criteria:

- Technical Evaluation (80 Points)

Only proposals scoring 60 points and above will qualify for financial evaluation.

| S/No | Criteria | Maximun Score |
| --- | --- | --- |
| 1 | Understanding of the Assignment | 10 |
| 2 | Methodology and Approach | 25 |
| 3 | Work Plan and Timelines | 10 |
| 4 | Relevant Experience | 15 |
| 5 | Team Composition and Expertise | 10 |
| 6 | Quality Assurance and Risk Mitigation | 05 |
| 7 | Added Value / Innovativeness | 05 |

- Financial Evaluation (20 Points)

The lowest evaluated financial proposal will receive the maximum score of 20. Other proposals will be scored proportionally as follows. Financial Score = lowest PriceProposed Price × 20

- Combined Evaluation

Total Score = Technical Score + Financial Score

The highest-ranked proposal will be recommended for contract award.

14. Additional Information

- AFSA reserves the right to accept or reject any application without assigning reasons.

- Only shortlisted applicants will be contacted.

- AFSA may request presentations or interviews as part of the evaluation process.

- Applications that do not comply with the submission requirements may be disqualified.

- All data, reports, and outputs produced under this assignment shall remain the property of AFSA. The consultant shall not publish or share outputs without prior written consent.

- Consultants must disclose any actual or potential conflict of interest

15. AFSA Commitment

AFSA is committed to equity, inclusion, and safeguarding and encourages applications from diverse and gender-balanced teams, including regional experts.

16. Requests for Clarification

Requests for clarification may be submitted to afsa@afsafrica.org or nicholas.omoding@afsafrica.org